## product backlog
Title/User Story | Description/Activity | Prio (1 = high) | Status | Start Date | Est Time (weeks or days) | Estimated Time S/M/L (1d/2d/3d) | Days | Actual Time | Planned Sprint | Comment
Record | Record sounds with the device microphone. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Limitation at 1 minute. Notification if you leave the record.
Record sources | the user will be able to record from the internal or an external microphone | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 |  |  | none
Buffer Record | Temporarely store the audio | 2 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | find the best way to store audio during record
save record | save the file in the default folder | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 | 0 |  | none
Interface | Multi-device layout (tablet 7 inch and mobile phone) | 1 | Ongoing | 30/12/13 | 3 | l | 3 | 0 | x | Easy access to basic functions. 3 layouts.
Manage / storage | Store the record on the SD card. You can choose where and different format. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Store the file in different formats, rename it, delete it and choose where you want store it.
Play | send the audio to an external media player | 3 | Ongoing | 30/12/13 | 0,5 | s | 0,5 |  |  | we can use an external player for play, pause and stop to listening the file
Share | The record file can be share with another device. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | The file can be send by mail, Bluetooth….
Settings | Change the default file storage, and the format | 3 | Ongoing | 30/12/13 | 1 | s | 1 | 0 |  | Interface to easily change every settings

## Sprint backlog
Title/User Story | Description/Activity | Priority (1 = high) | Estimated Time | Started/used | Completion used | Developer | Status | Week | Comment
Record | Record sounds with the device microphone. | 1 | 1 |  |  | XIAO KAI | Ongoing | 0 | Limitation at 1 minute. Notification if you leave the record.
Buffer Record | Temporarely store the audio | 2 | 1 |  |  | Yuyi | Ongoing | 0 | Find the best way to store audio during record
Record sources | the user will be able to record from the internal or an external microphone | 3 | 0,5 |  |  | SUN Hao | Ongoing |  | none
save record | save the file in the default folder | 3 | 0,5 |  |  | XIAO KAI | Ongoing | 0 | none
Interface | Multi-device layout (tablet 7 inch and mobile phone) | 1 | 3 |  |  | Maitre Robin | Ongoing | 0 | Easy access to basic functions. 3 layouts.
Manage / storage | Store the record on the SD card. You can choose where and different format. | 1 | 1 |  |  | Yann Vaillant | Ongoing | 0 | Store the file in different formats, rename it, delete it and choose where you want store it. You can call a media player for play the file.
Share | The record file can be share with another device. | 1 | 1 |  |  | FENG Changhong | Ongoing | 0 | The file can be send by mail, Bluetooth….
Play | send the audio to an external media player | 3 | 0,5 |  |  | Yuyi | Ongoing |  | we can use an external player for play, pause and stop to listening the file
Settings | Change the default file storage, and the format | 3 | 1 |  |  | SUN Hao | Ongoing | 0 | Interface to easily change every settings