## product backlog
Description | Column1 | Prio | Status | Column2 | Column3 | Column4 | Column5 | Column6 | Column8 | Column9
Title/User Story | Description/Activity | Prio (1 = high) | Status | Start Date | Est Time (weeks or days) | Estimated Time S/M/L (1d/2d/3d) | Days | Actual Time | Planned Sprint | Comment
Record | Record sounds with the device microphone. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Limitation at 1 minute. Notification if you leave the record.
Interface | Multi-device layout (tablet 7 inch and mobile phone) | 1 | Ongoing | 30/12/13 | 3 | l | 3 | 0 | x | Easy access to basic functions. 3 layouts.
Manage / storage | Store the record on the SD card. You can choose where and different format. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | Store the file in different formats, rename it, delete it and choose where you want store it. You can call a media player for play the file.
Share | The record file can be share with another device. | 1 | Ongoing | 30/12/13 | 1 | s | 1 | 0 | x | The file can be send by mail, Bluetooth….

## Sprint backlog
Title/User Story | Description/Activity | Priority (1 = high) | Estimated Time | Started/used | Completion used | Developer | Status | Week | Comment
Record | Record sounds with the device microphone. | 1 | 1 |  |  | dev | Ongoing | 0 | Limitation at 1 minute. Notification if you leave the record.
Interface | Multi-device layout (tablet 7 inch and mobile phone) | 1 | 3 |  |  | dev | Ongoing | 0 | Easy access to basic functions. 3 layouts.
Manage / storage | Store the record on the SD card. You can choose where and different format. | 1 | 1 |  |  | Vayan lama | Ongoing | 0 | Store the file in different formats, rename it, delete it and choose where you want store it. You can call a media player for play the file.
Share | The record file can be share with another device. | 1 | 1 |  |  | dev | Ongoing | 0 | The file can be send by mail, Bluetooth….