## New Requests
Description | Description |  |  |  |  | Prio | Status
System | Title/User Story | Description/Activity | One slider Link or feature brief document | Motivation/Business value | Origin | Prio (1 = high) | Status | Started | Estimated Time S/M/L (2d/1w/4w) | Days | Actual Time | Planned Sprint | Comment
Project_xxx or module_xxx | Show a flower based on status | Show a flower on each page based on the latest application status, current risk reported by APM and quality in latest tested version. | http://metadoc.sonyericsson.net/login_link.asp?doc=1/1220-1/FCP1190885&rev=latest | This would make all IA members happier and decisions will be better, increasing launch accuracy. | Hammer, Johan |  |  |  |  | 0
IAMS | Tree structure in reporting list | Some projects have many target products, we need a way to easily report on many projects. Proposed is a tree structure. See document for details. | http://metadoc.sonyericsson.net/?DOCS=4/0363-30/FCP1190885 | Will save time for PMs. Will improve overview of ongoing projects. | Markus Svenson (Supported by Steve Brown, Siska Alfredsson) |  |  |  |  | 0
Total | Total | 2 | [7 empty] | 0 |  |  | 0
Example
Add your request or suggestions here.

## Product Backlog
Description | [6 empty] | Prio | Status
ID | System | Title/User Story | Description/Activity | One slider Link or feature brief document | Motivation/Business value | Origin | Prio (1 = high) | Status | Start Date | Actual Effort Already Used | Est Time (weeks or days) | Estimated Time S/M/L (2d/1w/4w) | Days | Actual Time | Planned Sprint | Comment
CH1117001 | Report Tool | Change titles in reporting changes | Change the titles in the APM Status report for the delivery dates. | http://metadoc.sonyericsson.net/login_link.asp?doc=49/0360-LXE1100148&rev=latest |  | Hjärtquist, Håkan | 1 | Done |  |  |  |  | 0
CH1118001 | FP IAMS Sync 2.0 | Upgrade sync solution according proposal from tools team | Use C# batch to control whole sync process | http://metadoc.sonyericsson.net/?DOCS=1/15961-30/FCP1190885 | Increase stability, track problem easier | IA Tools | 1 | Ongoing | May |  | 2w | L | 20
CH1118002 | FP IAMS State Combine | Change states names phases/states | To align the names of the development states in FP and IAMS we would like to use the FP names in both tools. | http://metadoc.sonyericsson.net/login_link.asp?doc=2/15501-4/FCP1190885&rev=latest | This will get all a much better understanding of the status in the project dispite of which tool is used. It is a simple change and the first step of making the whole tool usage easier | Källmark, Nina | 1 | Ongoing |  |  |  |  | 0
CH1118003 | TMS | VPM Assignment The number of VPM resposible App | Page for maintaining VPM assignments (replacing excel tools) |  | The activity page is not used for VPM assignent | Bai, Freeman | 2 | Ongoing |  |  | 1w | M | 5
CH1118004 | TMS | Create verifaction tasks based on FP | Update the webpage according to VPMs' feedback |  |  | VPMs | 1 | Ongoing | March |  | 3w | l | 15 |  |  | Implemented in test.
CH1119001 | IAMS | Change department structure in IAMS | Change section names, exchange some people to other section |  |  | Johan Hammer | 1 | Ongoing | May |  | 1D | S
CH1119002 | Report Tool | Change the data fields validation logic | Change validation rule of APM status report tool |  |  | Grenner, Daniel | [6 empty] | 0
CH1124001 | Delivery Log | Implement Delivery Log in IAMS |  | http://metadoc.sonyericsson.net/login_link.asp?doc=2/1056-LXE1101506&rev=PA10 |  | Stålhammar, Fredrik | [6 empty] | 0
| IAMS FP Sync | Increase stability by using transaction id’s | [17.5] Hold on this item due to FP IAMS Sync solution 2.0 1. Add SP and Transaction number field into sync tables (default value = NULL) 2. Add transaction table 3. Request FP team to update Java program, confirm are tables filled. 4. Change so sync is done only on completed record sets based on transactions |  | This is critical for stability of IAMS basic data. | Brown, Steve | 1 | On Hold | March |  | 2w | L | 10 |  |  | Blocked by IS/IT
| All | Persons should be clickable with link | Name (note name should be clickable from SEConnect e.g. for me this link should be possible to add: http://seconnect.sonyericsson.net/Employees/EmployeeProfile.aspx?accountname=CORPUSERS\23044473 |  |  | Mats | 5 |  |  |  | 2w | L | 20
Total |  | 10 | [10 empty] | 70 |  |  | 2

## Sprint backlog
ID | Project Office or site | Sub Category | Title/User Story | Description/Activity | Priority (1 = high) | Estimated Time | Started/used | Completion used | Developer | Status | Week | Origin | Comment
| Tool | Report | Edit platform summary details | Save escalation comments into platform summary detail table | 1 | 4 | 4 |  |  | Done |  | Olsson, Stefan
| Tool | Report | Create reports | Understanding common report data selection criterira, temporary tables etc | 1 | 4 | 4 |  |  | done
| Tool | Verification Resource | Connect resource tool with TMS tasks | Connect resource tool with TMS tasks | 1 | 32 |  |  | Xu, Zilong | Done |  |  | 12h remain
| Tool | Website | Move all small tools to website. | Build a website to handle all reports request. | 1 | 8 |  |  | Xu, Zilong | Done |  |  | 2h remains
| Tool | Website | Move all small tools to website. | TaskOfTC Tool VBA. | 1 | 6 |  | 8 | Xu, Zilong | Done
| TMS |  | Sync with Project Reporting db and TMS | Implement the data sync program. | 1 | 12 | 8 |  | Qin, Xiaobo | Cancel |  |  | 2h remains for deployment. Part of IAMS v2.0 scope.
| Tool | Report | Change Data structure | Change the data structure to enable simpler sync with TMS and FP | 1 | 20 |  |  |  | Done |  |  | Done
| Tool | Report | Sync with FP and Project Reporting db | Align data with FP and Project DB | 1 |  |  |  |  | Cancel |  |  | Part of IAMS v2.0 scope.
| TMS |  | Add the new "SEMC Verify" coverage. | Need to make some changes to the process for the new type of tasks. | 1 | 6 |  |  | Qin, Xiaobo | Cancel |  | Chen, Sindey | Cancelled, confirmed with Sindey
Total | [5 empty] | 92

## Done
System | Title/User Story | Description/Activity | Origin | Priority (1 = high) | Estimated Time | Started/used | Completion used | Developer | Status | Comment
External Viewer | Show defect status. | Add the defect status chart for Mimmi. |  | 4 | 6 |  |  | Xu, Zilong | Done
External Viewer | Update stucture of defect chart page | Update stucture of defect chart page for the purpose of updating chart queries easily. |  |  | 4 |  |  | Xu, Zilong | Done
Report Tool | Develop Web UI | Update UI based on Stefans feedback |  | 1 | 8 |  |  |  | Done
Report Tool | Verify Web UI | Update UI based on expected APM feedback |  | 1 | 12 |  |  |  | Done | needed again w1013
TMS | Main page with link collection | Create a main page for iatms.sonyericsson.net containing links/menues to all sub parts. |  | 2 | 8 |  |  | Xu, Zilong | Done
Project Cost Delivery | Add test project | Add test project which no need to separate by phase. | Feng, Gloira |  | 4 |  |  | Qin, Xiaobo | Done
Report Tool | Sync with FP | tool to sync projects between FP exporter/importer and Report Tool New. |  |  | 10 |  |  |  | Done
Report Tool | Sync with FP | Connect to FP via XML and extract data |  |  | 16 |  |  |  | Done
Report Tool | Sync with TMS | preparing for export to TMS |  |  | 5 |  |  |  | Done
Total |  |  |  |  | 73

## Action Log
When | Area | What | Who | ETA | Comment
1035.5 | SubPort | AP Matt (&Thomas): Make a code review of the Submission portal on Monday
1035.5 | SubPort | AP Matt: Setup a security review of the Submission Portal with Corporate IT.
1035.5 | SubPort | AP Thomas: Setup a meeting Tuesday or Wednesday to discuss feedback on the code and the UI.
1035.5 | SubPort | AP Matt & Thomas: Figure out how to send an email to the (correct) APM when a new upload has been made.
1036.5 | ExternalView | agree on layout. | Johan